|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| JANUARY | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 |
| RISK | **Phishing** Business Email Compromise (BEC) | **Phishing**Ransomware |
| POLICY | **Anti-Phishing** **Policy** | **Review** Policy Adoption |
| ­­  REMEDIATION | **Phishing eLearning** | **Review** Learning Adoption | **Phishing Simulation** | **Review** Phishing Simulation Adoption |
|   MEASUREMENT | **Test****of Understanding** | **Review** **Test** **Results** | **Click /****Data Entry Rates** | **Review Results** |
| ­­DISSEMINATION | **Email Notification**Enforce - MetaEngage**Collate & Share Results** | Deliver Across a Number of Days / Hours or all at Once.**Collate & Share Results** |
| SECONDARYREMEDIATION | **Business Email Compromise** (BEC) Blog | **Posters / Screensaver** | **Ransomware Blog** | **Phishing Blog / Stats** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| APRIL | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 |
| RISK | **Incident Reporting** |
| POLICY | **Incident Reporting Policy** | **Review** Policy Adoption |
| ­­  REMEDIATION | **Incident Reporting / Threats eLearning** | **Review** Learning Adoption | **Phishing Simulation** | **Review** Phishing Simulation Adoption |
|   MEASUREMENT | **Test****of Understanding** | **Review** **Test** **Results** | **Click /****Data Entry Rates** | **Review Results** |
| ­­DISSEMINATION | **Email Notification**Enforce - MetaEngage**Collate & Share Results** | Deliver Across a Number of Days / Hours or all at Once.**Collate & Share Results** |
| SECONDARYREMEDIATION | **Screensaver** | **Poster** | **Blog Post** Password Recovery | **Blog Post** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| FEBRUARY | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 |
| RISK | **Physical Security**Tailgating / Access Control |
| POLICY | **Tailgating /****Access****Control Policy** | **Review**Policy Adoption |
| ­­ REMEDIATION | **Access Control eLearning** | **Review** Learning Adoption | **Phishing Simulation** Capture Password Details | **Review** Phishing Simulation Adoption |
| MEASUREMENT | **Test****of Understanding** | **Review****Test****Results** | **Click /****Data Entry Rates** | **Review Results** |
| ­­DISSEMINATION | **Email Notification**Enforce - MetaEngage**Collate & Share Results** | Deliver Across a Number of Days / Hours or all at Once.**Collate & Share Results** |
| SECONDARYREMEDIATION | **Screensaver** | **Poster**/Tailgating | **Blog Post** Physical Sec /Access Control | **Blog Post** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| MAY | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 |
| RISK | **Social Engineering**Vishing, Smishing, Cybercrime |
| POLICY | **Social Engineering** Policy / Guidelines | **Review**Policy Adoption |
| ­­ REMEDIATION | **eLearning** SE / Vishing / Smishing | **Review** Learning Adoption | **Phishing Simulation** | **Review** Phishing Simulation Adoption |
| MEASUREMENT | **Test****of Understanding** | **Review****Test****Results** | **Click /****Data Entry Rates** | **Review Results** |
| ­­DISSEMINATION | **Email Notification**Enforce - MetaEngage**Collate & Share Results** | Deliver Across a Number of Days / Hours or all at Once.**Collate & Share Results** |
| SECONDARYREMEDIATION | **Screensaver** | **Poster** | **Blog Post** | **Blog Post** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| MARCH | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 |
| RISK | **Passwords** Credential Hygiene |
| POLICY | **Account Credentials** Policy / Guidelines | **Review** Policy Adoption |
| ­­  REMEDIATION | **Password Safety eLearning** | **Review Learning Adoption** | **Phishing Simulation**  | **Review** Phishing Simulation Adoption |
|   MEASUREMENT | **Test****of Understanding** | **Review** **Test** **Results** | **Click /****Data Entry Rates** | **Review Results** |
| ­­DISSEMINATION | **Email Notification**Enforce - MetaEngage**Collate & Share Results** | Deliver Across a Number of Days / Hours or all at Once.**Collate & Share Results** |
| SECONDARYREMEDIATION | **Screensaver** | **Poster** | **Blog Post** Password Recovery | **Blog Post** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| JUNE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 |
| RISK | **Bribery Awareness** |
| POLICY | **Anti-Bribery** **& Corruption Policy** | **Review** Policy Adoption |
| ­­  REMEDIATION | **eLearning**Anti-Bribery | **Review** Learning Adoption | **Phishing Simulation** | **Review** Phishing Simulation Adoption |
|   MEASUREMENT | **Test****of Understanding** | **Review** **Test** **Results** | **Click /****Data Entry Rates** | **Review Results** |
| ­­DISSEMINATION | **Email Notification**Enforce - MetaEngage**Collate & Share Results** | Deliver Across a Number of Days / Hours or all at Once.**Collate & Share Results** |
| SECONDARYREMEDIATION | **Screensaver** | **Poster** | **Blog Post** | **Blog Post** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| JULY | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 |
| RISK | **Social Media Safety** |
| POLICY | **Social Media Guidelines** | **Review** Policy Adoption |
| ­­  REMEDIATION | **Social Media eLearning** | **Review** Learning Adoption | **Phishing Simulation** | **Review** Phishing Simulation Adoption |
|   MEASUREMENT | **Test****of Understanding** | **Review** **Test** **Results** | **Click /****Data Entry Rates** | **Review Results** |
| ­­DISSEMINATION | **Email Notification**Enforce - MetaEngage**Collate & Share Results** | Deliver Across a Number of Days / Hours or all at Once.**Collate & Share Results** |
| SECONDARYREMEDIATION | **Screensaver** | **Poster** | **Blog Post** | **Blog Post** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| OCTOBER | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 |
| RISK | **ISO Awareness** |
| POLICY | **ISO** **Policies** | **Review** Policy Adoption |
| ­­  REMEDIATION | **ISO** **eLearning** | **Review** Learning Adoption | **Phishing Simulation** | **Review** Phishing Simulation Adoption |
|   MEASUREMENT | **Test****of Understanding** | **Review** **Test** **Results** | **Click /****Data Entry Rates** | **Review Results** |
| ­­DISSEMINATION | **Email Notification**Enforce - MetaEngage**Collate & Share Results** | Deliver Across a Number of Days / Hours or all at Once.**Collate & Share Results** |
| SECONDARYREMEDIATION | **Screensaver** | **Poster** | **Blog Post** | **Blog Post** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| AUGUST | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 |
| RISK | **GDPR** |
| POLICY | **GDPR** **Policy** | **Review** Policy Adoption |
| ­­  REMEDIATION | **GDPR eLearning** | **Review Learning Adoption** | **Phishing Simulation**  | **Review** Phishing Simulation Adoption |
|   MEASUREMENT | **Test****of Understanding** | **Review** **Test** **Results** | **Click /****Data Entry Rates** | **Review Results** |
| ­­DISSEMINATION | **Email Notification**Enforce - MetaEngage**Collate & Share Results** | Deliver Across a Number of Days / Hours or all at Once.**Collate & Share Results** |
| SECONDARYREMEDIATION | **Screensaver** | **Poster** | **Blog Post** | **Blog Post** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| NOVEMBER | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 |
| RISK | **CIA / Information Security** |
| POLICY | **Account Credentials** Policy / Guidelines | **Review** Policy Adoption |
| ­­  REMEDIATION | **CIA Guidelines****/ Policy** | **Review Learning Adoption** | **Phishing Simulation**  | **Review** Phishing Simulation Adoption |
|   MEASUREMENT | **Test****of Understanding** | **Review** **Test** **Results** | **Click /****Data Entry Rates** | **Review Results** |
| ­­DISSEMINATION | **Email Notification**Enforce - MetaEngage**Collate & Share Results** | Deliver Across a Number of Days / Hours or all at Once.**Collate & Share Results** |
| SECONDARYREMEDIATION | **Screensaver** | **Poster** | **Blog Post** | **Blog Post** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| SEPTEMBER | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 |
| RISK | **Multi-Factor Authentication** |
| POLICY | **MFA** **Policy** | **Review** Policy Adoption |
| ­­  REMEDIATION | **MFA eLearning** | **Review Learning Adoption** | **Phishing Simulation**  | **Review** Phishing Simulation Adoption |
|   MEASUREMENT | **Test****of Understanding** | **Review** **Test** **Results** | **Click /****Data Entry Rates** | **Review Results** |
| ­­DISSEMINATION | **Email Notification**Enforce - MetaEngage**Collate & Share Results** | Deliver Across a Number of Days / Hours or all at Once.**Collate & Share Results** |
| SECONDARYREMEDIATION | **Screensaver** | **Poster** | **Blog Post** | **Blog Post** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| DECEMBER | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 |
| RISK | **Mobile App Security** |
| POLICY | **Mobile Device Policy** | **Review** Policy Adoption |
| ­­  REMEDIATION | **Mobile** **Device / App eLearning** | **Review Learning Adoption** | **Phishing Simulation**  | **Review** Phishing Simulation Adoption |
|   MEASUREMENT | **Test****of Understanding** | **Review** **Test** **Results** | **Click /****Data Entry Rates** | **Review Results** |
| ­­DISSEMINATION | **Email Notification**Enforce - MetaEngage**Collate & Share Results** | Deliver Across a Number of Days / Hours or all at Once.**Collate & Share Results** |
| SECONDARYREMEDIATION | **Screensaver** | **Poster** | **Blog Post** | **Blog Post** |